## Assessment group
Assessment Group: Planning and Interventions Calendar
S.No | Activity | Key points discussed | Department Approval | Roles & Responsibilities | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Diagnostic / Baseline Assessment
1 | Create an Assessment cell with representatives from SCERT, DIET and Schools (Principals and teachers) , Assessment experts, data analysts and curriculum experts to work on assessment plans | Some of the responsibilities of the team will be a. Securing administrative approvals/support b. Research on best practices in other states. c. Work as the nodal agency for interacting with NCERT LO and CCE team. d. Detailing out each component of each of the types of assessments e. Creating rubrics, reporting formats, marking scheme etc. in alignment with CCE guidelines f. Training teachers on the framework g. Implementation of the framework in the state | Approval required for creation of an Assessment Cell and to authorize the selected team members to work on assessment plans | 1. SCERT to identify existing state level champions within the department and partner organizations 2. Formally engage with NCERT (or relevant national assessment govt/non-gov bodies) 3. Onboard consultants for positions such as data analyst and project managers (optional) | bar: Mar
2 | Identify all ongoing assessment programmes in the state to create synergistic activities | No uniformity in the type/mode of assessment conducted by the state. The report card format also varies from district to district.
3 | Create a common state wide assessment framework and calendar | There is a need for a Standardized Assessment Framework and calendar which will include Formative assessments, Mission LOC and Summative assessments. Apart from this a quarterly assessment of teachers for professional development should also be conducted in coordination with the Transactional Core team | Approval for developing a Standardized Assessment Framework and calendar to check the progress of learning in all schools in the state Also need approval to bring flexibility in implementing the CCE framework | Assessment cell | bar: Mar
4 | Detail out process for state wide diagnostic test to be conducted in April | SA2 to be taken as the baseline / diagnostic assessment and will be done for all students / all classes / all subjects. |  | Assessment cell | bar: Mar
5 | Prepare assessment items for diagnostic / baseline assessment and teacher training | The SA2 question papers to be designed keeping the required LOs for that particular class. Class 5 and 8 have board exams | Approval for conducting SA2 at one time in the entire state for a uniform testing | Assessment cell | bar: Mar
6 | Roll out diagnostic assessment - SA2 | To keep the marking fair , the papers to be checked by teachers of neighboring schools | Approval for the teachers to be available for the corrections at the Block level at the same time | Assessment Cell / Block level/ School Principals | Apr: Base line; Jun: Mid line; Jun: End line
7 | Capture and analyze results | The diagnostic test should be able to identify actual learning level of student. The result of each student to be analyzed and the data to be made available to the respective teachers so that teaching strategies can be planned out for the new academic session. | The data of each student to be made available to the teachers / at block level/ at state level. Also the results of this test should be fed into LO app so that relevant LOs are targeted for each student for the next academic year | Assessment Cell / Block level/ School Principals | bar: May
Formative assessment | Formative Assessment
8 | To develop a plan for continuous 'Assessment for learning' | It is important to assess students on a daily basis students on areas such as reading, speaking, values, 21st century skills etc. These skills are not be marked and should only be used for improving learning levels |  | Assessment cell | bar: Mar
9 | Creating Rubrics for formative assessment | Rubrics to be created for various activities that can be used to assess students such as : 1.Project work - scrapbook etc. 2. Quiz (Oral/Written) 3. Story writing 4. Homework evaluation 5. Reading tests 6. Group work 7. Competitions such as debate, declamation | Approval for creating booklets for each student detailing various formative assessments | Assessment cell and team of selected teachers | bar: Mar; May
10 | Roll-out "Assessment for learning" | Training to be given to the teachers about using the booklets and rubrics before the new session begins |  | Assessment cell in coordination with the Transactional core team to train teachers Subject teachers of respective schools to administer the assessments | bar: May; July to Oct; Dec to Mar; July to Oct; Dec to Mar
Mission LOC - Periodic assessments | Mission LOC - Periodic Assessments
11 | To develop a plan and rubrics for "Mission LO Completion" | In coordination with the transactional group , learning outcomes (month wise ) to be clearly stated for each subject |  | Assessment cell in coordination with Transactional core team | bar: Mar
12 | Create an app for 'Mission LOC' (LO app) | The idea is to create an LO app through which teachers can administer periodic assessments on targeted learning outcomes for all students a. A detailed FRS to be prepared for the same b. Engage with team at NIC/CHiPS for app development | To sanction budget for creating LO app | Assessment cell in coordination with the IT team | bar: Mar to May
13 | Roll out 'Mission LOC' through LO app | Training to be given to the teachers about using the LO App before the new session begins. a. Focus learning outcomes(LOs) will be determined for each month by the Core team b. In the last week of every month, all the headmasters will be sent ten questions based on ten different LOs for each class on their mobile phones. c. Using the app, the teachers can administer the assessment and data will get collected. d. Based on data, recommended teaching practices/videos/training modules to be made available for teachers |  | Assessment cell in coordination with the Transactional core team to train teachers Principals and Subject teachers of respective schools to administer the assessments | bar: July to Oct; Dec to Mar; July to Oct; Dec to Mar
Summative assessments | Summative Assessments
14 | Develop Summative assessment plan | To assess students on desired learning outcomes from the curriculum taught , summative assessment to be conducted twice in a year. This should be a uniform pattern in the entire state of maximum marks / number of questions for each subject A common report card format also needs to be developed . |  | Assessment Cell
15 | Develop question papers based on the required LOs | The core idea is to move from lower order thinking skills(LOTS) to higher order thinking skills(HOTS). This will also cater to the different ability groups. |  | Assessment Cell
16 | Roll out Summative Assessments | Training to be given to the teachers about Summative assessments before the new session begins. |  | Assessment cell in coordination with the Transactional core team to train teachers
Professional development of teachers | Professional development of teachers
17 | Develop a plan for professional development through self-assessment using technology and classroom observations on a quarterly basis | A plan for the professional development of teachers through self-assessment needs to be developed covering aspects such as: a. Content b. Pedagogy c. Classroom management d. ICT e. Planning f. Leadership g. Digital literacy h. LOs i. TLM usage | To provide relevant training support to the teachers for their professional development and learning | Assessment cell in coordination with the Transactional core team | bar: May; Oct; Mar; Oct; Mar
NEW SESSION
HALF YEARLY EXAMS
FINAL EXAMS
NEW SESSION
HALF YEARLY EXAMS
FINAL EXAMS
NEW SESSION
HALF YEARLY EXAMS
FINAL EXAMS
FINAL EXAMS
NEW SESSION
FINAL EXAMS
FINAL EXAMS
FINAL EXAMS
FINAL EXAMS
NEW SESSION
HALF YEARLY EXAMS
HALF YEARLY EXAMS
HALF YEARLY EXAMS
NEW SESSION
NEW SESSION
NEW SESSION
NEW SESSION
NEW SESSION
NEW SESSION
NEW SESSION
NEW SESSION
NEW SESSION
NEW SESSION