## Sheet1
Baseline Assessment
S.No. | Activity | Detailed inputs | Roles and Responsibilities | Feb | Mar | Apr | May | Jun | July
1 | Setting of the Question Papers | The Q papers to be set based on the specified learning outcomes for each class keeping the same pattern ( Knowledge based - 20% , Understanding based-40% , Application based - 30% , HOTS - 10%) | Core Academic team-Assessment Cell | [6 empty] | Key
a | Class 1, 2, 3 and 4 | 50 marks / 2 hrs. | [8 empty] | Already in progress / scheduled | bar: Mar
b | Class 5 (Board Exams) | As per the Board pattern 100 marks /2 hrs. | [8 empty] | Yet to be started | bar: Feb
c | Class 6 and 7 | 50 marks / 2.5 hrs. | bar: Mar
e | Class 8 (Board Exams) | As per the Board pattern 100 marks /2.5 hrs. | bar: Feb
f | Class 9 and 11 | As per the Board pattern 100 marks / 3 hrs. | bar: Mar
g | Class 10 and 12 (Board Exams) | As per the Board pattern 100 marks / 3 hrs. | bar: Feb
2 | Printing of Question papers and blank answer sheets | Class 1-8 - The question papers have spaces for writing the answers Class 9-12 - The answer sheets have to be provided separately | Samagra Shiksha | bar: Feb to Mar
3 | Distribution of Question Papers (District / Block wise) |  | Samagra Shiksha | bar: Mar
4 | Exam schedule | Board Exams for Class 5 , 8 , 10 and 12 | Samagra Shiksha | bar: Mar
|  | Common date sheet/ calendar across the State for Classes 1,2,3,4,6,7,9 and 11 | Samagra Shiksha | bar: Apr
5 | Correction of answer sheets | At Block level…teachers to correct answer sheets of neighboring schools | Teachers | bar: Apr to May
6 | Data entry | At Block level -Question-wise data entry to be done | Teachers/ SPOC nominated by DEO | bar: May
7 | Analysis of data | Data to be analyzed question wise to understand the gaps in learning . This data is to be made available to the teachers so that they can plan their strategies for the new academic session | Core Academic team-Assessment Cell | bar: Jun
8 | Final Report | Class-wise report on the gaps which will help strategies for the next academic year | Core Academic team-Assessment Cell | bar: Jun to July